## Specifications SQA
Specifications SQA
Date SQA'd | SQA'd by | Section | Version | Correction Needed | Status | Action Taken | Corrected by | Corrected on
2021-02-20 | David Brown | 1.2 | 1 | Will the website echoing data from the data base or displayed in a new way? | Fixed | Specified the purpose of the site and what will be done with the acquired data, how it is displayed in a new way | Lakshmi | 2021-04-02
2021-02-20 | David Brown | 2.2 | 1 | Where would the frequently asked questions come from? Are they from this app or from the infobase website | Fixed | Included more in-depth detail about FAQ page's functionality | Lakshmi | 2021-04-02

## SPMP SQA
SPMP SQA
Date SQA'd | SQA'd by | Section | Current Version | Correction Needed | Status | Action Taken | Corrected by | Corrected on
2021-02-02 | Zach, Amari | 6.1 | 1 | Process Models needs to be elaborated on | Fixed | Improved 6.1 and added descriptions | Bart | 2021-02-02
2021-02-02 | Maninder, Ryan | 1.3 | 1 | Innaccurate Project Deliverable Table | Fixed | Modified dates to match deadline dates | Maninder, Ryan | 2021-02-02
2021-02-03 | Maninder, Ryan | 5.1, 5.2, 5.3 | 1 | Inconsistancies throughout document | Fixed | Modified fomation to stay consistant | Kevin | 2021-02-04
2021-02-20 | David Brown | 1.3 | 1.1 | Should have more specifics about who is doing what SQA for what section. | Fixed | Role descriptions added to describe each the roles of each individual subteam | Evan | 2021-04-04
2021-04-04 | Liam | 4.1 | 1.1 | Internal Structures is out of date | Fixed | Updated the internal structures to match changes made to our progress in the creation of the COVIDaware website | Evan, Kevin | 2021-04-04
2021-04-04 | Evan | 4.2 | 1.1 | Roles and Responsibilities needs to be updated | Fixed | Updated Roles and Responsibilities to reflect changes in team structures | Evan | 2021-04-04
2021-04-04 | Kevin | 6.2 | 1.1 | Programming languages need to be updated after our last meeting | Fixed | Update to programming languages being used in implementation | Evan, Kevin | 2021-04-04
2021-04-04 | Evan | 7.1 | 1.1 | Update documentation | Fixed | Updated Documentation plan | Kevin, Raman | 2021-04-04
2021-04-04 | Liam | 7.2 | 1.1 | Quality Assurance Plan needs more clarity and detail | Fixed | Updated Quality Assurance Plan | Raman | 2021-04-04
2021-04-16 | Lakshmi | 1.3, 6.1 | 2 | Deliverable dates should be adjusted to reflect extensions | Fixed | Dates have been changed | Evan | 2021-04-16
2021-04-16 | Evan | 6.2 | 2 | Programming languages are out of date | Fixed | Updated to reflect implementation | Evan | 2021-04-16
2021-04-16 | Lakshmi | 7.3 | 2 | SPMP needs to be updated to reflect major software revisions | Fixed | Adding in a section to the SPMP that is responsible for detailing all major revisions | Evan | 2021-04-16
2021-04-16 | Maninder, Ryan | 7.3.1 | 2 | Search Bar removal needs to be mentioned | Fixed | Added Search Bar Problem Explanation | Evan, Maninder | 2021-04-16

## Requirements SQA
Requirements SQA
Date SQA'd | SQA'd by | Section | Current Version | Correction | Status | Action Taken | Corrected by | Corrected on
2021-02-10 | Raman | 2.6 | 1.1 | Use Case diagram requires altercations (turn into 2 seperate ones) | Fixed | Split use case diagram for clarity | Evan | 2021-02-11
2021-02-11 | Kevin | 2.6 | 1.1 | Use Case descriptions don' t match diagram | Fixed | Rewritten Use Case descriptions to match with the diagram | Evan | 2021-02-11
2021-02-21 | David Brown | 2.6 | 1.2 | Extend' relationships should use the triangle relationship, inconsistencies | Fixed | Recreated Use Case diagrams to align with the feedback provided by David Brown | Kevin, Evan, Raman | 2021-04-04
2021-04-04 | David Brown | 2.6 | 1.2 | Use Case descriptions inconsistent with diagrams | Fixed | Rewritten Use Case descriptions to match with the newly updated diagram | Kevin, Evan, Raman | 2021-04-04
2021-04-06 | Kevin | 1.3 | 1.2 | Missing information from newly updated SPMP | Fixed | Updated defintions to match information added to SPMP | Raman | 2021-04-04
2021-04-16 | Kevin | 1.3 | 2 | Delete info regarding database | Fixed | Deleted database information | Asad | 2021-04-16
2021-04-16 | Kevin | 2.6 | 2 | Update use case description regarding database | Fixed | Updated use case description regarding database | Asad | 2021-04-16
2021-04-16 | Kevin | 3.6 | 2 | Update from database to JSON | Fixed | Update from database to JSON | Asad | 2021-04-16
2021-04-16 | Kevin | 2.6 | 2 | Update from database to JSON | Fixed | Update from database to JSON | Asad | 2021-04-16

## Analysis SQA
Analysis SQA
Date SQA'd | SQA'd by | Section | Current Version | Correction Needed | Status | Action Taken | Corrected by | Corrected on
2021-03-01 | David Brown | 2.1, 2.2, 2.3 | 1 | Following up on advice given By David Brown regarding Entity, Boundary, and Control | Fixed | Removed control objects, and updated Entity and Boundary Objects | Keven, Evan, Raman | 2021-03-01
2021-03-03 | Kevin | 3.3 | 1 | Class Diagram missing | Fixed | Class Added to Planning document for Processing | Raman | 2021-03-04
2021-03-14 | David Brown | 2.2 | 2 | Inconsistent faqView and faqContent spelling between diagram and tables. | Fixed | Fixed inconsistent faqView and faqContent spelling between diagram and tables. | Maninder, Ryan | 2021-03-31
2021-03-14 | David Brown | 2.3 | 2 | No control objects | Fixed | Added control objects based on David Brown's suggestion | Maninder, Ryan | 2021-03-31
2021-03-14 | David Brown | 3.3 | 2 | Class Diagram does not make sense | Fixed | Added new Class Diagram used in Design Document | Maninder, Ryan | 2021-03-31
2021-03-14 | Maninder | 3.2 | 2 | Inconsistency with new class diagram | Fixed | Made all objects consistent with new diagram | Maninder, Ryan | 2021-03-31
2021-03-14 | David Brown | 4 | 2 | Move Appendix A down to bottom | Fixed | Move Appendix A down to botton | Maninder, Ryan | 2021-03-31
2021-03-14 | David Brown | 4 | 2 | No hyperlink for appendix a | Fixed | Created a hyperlink to Appendix A, and in Table of Contents | Maninder, Ryan | 2021-03-31

## Implementation SQA
Implementation SQA
Date SQA'd | SQA'd by | Version | Correction | Status | Action Taken | Corrected by | Corrected on
2021-04-16 | Maninder | 1 | Last Updated Bar at the bottom moves with scroll bar | Fixed | Made component for footer and updated CSS | Kyle | 2021-04-16
2021-04-16 | Kevin | 1 | Saskatchewan spelling error in canada pie graph | Fixed | Changed Data value to correct spelling | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Heatmap spelled wrong, "Heapmap" | Fixed | Fixed spelling in the H4 tag | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Kevin | 1 | On team page there are some errors with team member info (names/email) | Fixed | Updated Kevins name and Email in Team.js | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Ryan | 1 | Graph 'Cases, Fatalities and Recoveries in the past 7 days' x axis title is "2021-04-10" should be Date | Fixed | Updated hAxis.title option to Date | Ryan,Kyle,Zach,Bart | 2021-04-16 | Found
2021-04-16 | Zach | 1 | Inconsistencies with chart titles | Fixed | Changed all chart horzontal titles to "Date" | Ryan,Kyle,Zach,Bart | 2021-04-16 | In Progress
2021-04-16 | Maninder | 1 | Missing Dates Title in X-Axis for "Changes in Hospitalizations and Critical in the Past 7 Days" | Fixed | Added a horzontal title to "Changes in Hospitalizations and Critical in the Past 7 Days" graph | Ryan,Kyle,Zach,Bart | 2021-04-16 | Fixed
2021-04-16 | Kevin | 1 | "Number of vacines vs vacinated in the Past 7 Days" spelling error on all provincal (and national) pages | Fixed | Corrected spelling error | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Asad | 1 | Missing period in FAQ question 4 | Fixed | Added missing period | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Total COVID-19 Cases per Province, Manitoba spelt wrong | Fixed | Fixed Spelling Within home.js | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Last Updated on Homepage showing tommorow's date | Fixed | Updated "Last Updated" to current day(2021-04-16) | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Number of New Hospitalizations as of Today: currently shows a negative value (on Canada page) | Fixed | Discussed and Noted its not an issue | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | Minor grammar fix; in FAQs under What is COVID-19?, "virus was found(2019)" should be "virus was found (2019)." | Fixed | Added space after found | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | Add GitHub links to the Team section | Fixed | Updated Team section with everyones GitHub | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | Minor text fix; in FAQs under What does Green Zone mean?, "Indoor and Outdoor dining" should be "Indoor and outdoor dining" | Fixed | Lower case outddor in FAQ | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | Minor text fix; in FAQs under What does Red Zone mean?, "prohibited.Supermarkets" needs a space | Fixed | Added space after sentence | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Kevin | 1 | Switch "Cases, Fatalities and Recoveries in the past 7 days" to "Total Cases, Fatalities and Recoveries in the Past 7 Days" title within all graphs | Fixed | Added "Total" to the title to make it more direct | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Kevin | 1 | Switch "Hospitalizations VS Recoveries" to "Hospitalizations vs. Recoveries" title within all graphs | Fixed | Lower cased vs | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | The About page still mentions "All data on the COVIDaware website is from the Canadian government website for COVID-19". Should probably be amended to be more accurate. | Fixed | Fixed the sentence and made it more accurate | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1 | Under Changes in Hopsitalizations on the Canada page, today's Critical number is 200+ times too large | Fixed | variable misassigned, updated variable fixing the issue | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Kevin | 1 | Create a notice for the last time each information set was updated (all provinces/canada) | Fixed | Created a notice that displays when teh JSON is updated | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Heatmap when hovering over province says "total cases", switch to "New Cases" | Fixed | Changed variable to be more accurate. Now it is new cases. | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1 | Search Bar unable to get it to work | Fixed | Removed Search Bar | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Maninder | 1.1 | Last Updated Bar occasionaly will react in an unprediactable manner | Unresolved | N/A | N/A | N/A
2021-04-16 | Kevin | 1.1 | Vaccines distrupted graphs appear to be displaying the wrong info | Fixed | Changed pulled data from"change_vaccines_distributed" to "change_vaccinations:" | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Evan | 1.1 | Under Team, my email is spellled wrong, should be "attf7010@mylaurier.ca" | Fixed | Updated email to correct Email | Ryan,Kyle,Zach,Bart | 2021-04-16
2021-04-16 | Ahmar | 1.1 | Spelling inconsistency with Green Zone and Orange Zone paragraphs. Definitions should be capitalized. | Fixed | Capitalized "prevent" and "restrict" for consistency | Ryan,Kyle,Zach,Bart | 2021-04-16